## The 100 Tasks Checklist
The 100 Tasks Checklist
Tasks to complete |  |  |  | Implementation |  |  | Timeline
# | Stage | Sub-Stage | Task | Link to Sheet | Note / Comment | Owner | Start Week | End Week | Start Date | Planned End Date | End Date | Delay Days | Status
1 | SETUP | Start with Problems | Identify Problems and Trends |  |  |  | 1 | 1 |  |  |  | 0
2 | SETUP | Start with Problems | Evaluate Problems and Trends |  |  |  | 1 | 1 |  |  |  | 0
3 | SETUP | Start with Problems | Select Problem to Focus on |  |  |  | 1 | 1 |  |  |  | 0
4 | SETUP | Start with Problems | Pinpoint Pain Points and Determine Jobs to Be Done |  |  |  | 2 | 2 |  |  |  | 0
5 | SETUP | Plan Mission | Define Overall Vision, Mission, and Core Values |  |  |  | 2 | 2 |  |  |  | 0
6 | SETUP | Plan Mission | Gather All Steps |  |  |  | 3 | 3 |  |  |  | 0
7 | SETUP | Plan Mission | Streamline Steps |  |  |  | 3 | 3 |  |  |  | 0
8 | SETUP | Assemble Core Teams | Master Founder Fundamentals |  |  |  | 2 | 6 |  |  |  | 0
9 | SETUP | Assemble Core Teams | Round out Founding Team |  |  |  | 1 | 6 |  |  |  | 0
10 | SETUP | Assemble Core Teams | Secure Mentorship |  |  |  | 1 | 5 |  |  |  | 0
11 | SETUP | Collect Ideas | Decide on One of “Three Horizons” |  |  |  | 3 | 3 |  |  |  | 0
12 | SETUP | Collect Ideas | Transfer Proven Business Models to Ecosystems of Future Growth |  |  |  | 3 | 3 |  |  |  | 0
13 | SETUP | Collect Ideas | Generate “Long List” of Ideas |  |  |  | 3 | 3 |  |  |  | 0
14 | SETUP | Collect Ideas | Distill into “Short List” |  |  |  | 4 | 4 |  |  |  | 0
15 | SETUP | Determine Business Model | Compare How to Innovate (“10 Types of Innovation” for “Short List”) |  |  |  | 4 | 5 |  |  |  | 0
16 | SETUP | Determine Business Model | Compare How to Compete in “Blue Ocean” for “Short List” |  |  |  | 4 | 5 |  |  |  | 0
17 | SETUP | Determine Business Model | Compare Using “Business Model Canvas” for Short List |  |  |  | 4 | 5 |  |  |  | 0
18 | SETUP | Determine Business Model | Compare Using “Customer Discovery” |  |  |  | 4 | 5 |  |  |  | 0
19 | SETUP | Determine Business Model | Rank Business Models on “Short List” |  |  |  | 5 | 6 |  |  |  | 0
20 | SETUP | Determine Business Model | Build and Adapt Proof of Concept of #1 Business Model |  |  |  | 5 | 6 |  |  |  | 0
21 | SETUP | Determine Business Model | Define Your USPs |  |  |  | 5 | 6 |  |  |  | 0
22 | SETUP | Determine Business Model | Assemble Focus Group and Follow “Lean Startup” Loop Until Achieving “Customer Validation” |  |  |  | 3 | 20 |  |  |  | 0
23 | SETUP | Determine Business Model | Ensure ESG Compliance |  |  |  | 6 | 7 |  |  |  | 0
24 | SETUP | Determine Business Model | Build Financial Model |  |  |  | 4 | 6 |  |  |  | 0
25 | SETUP | Determine Business Model | Create Pitch Deck |  |  |  | 5 | 6 |  |  |  | 0
26 | LAUNCH | Develop MVP | Specify MVP |  |  |  | 7 | 9 |  |  |  | 0
27 | LAUNCH | Develop MVP | Determine Tool Stack |  |  |  | 7 | 9 |  |  |  | 0
28 | LAUNCH | Develop MVP | Setup Lean PMO |  |  |  | 7 | 7 |  |  |  | 0
29 | LAUNCH | Develop MVP | Perform Legal Check of Business Model and Key Documents |  |  |  | 7 | 8 |  |  |  | 0
30 | LAUNCH | Develop MVP | Calculate Costs for MVP Development |  |  |  | 8 | 8 |  |  |  | 0
31 | LAUNCH | Develop MVP | Develop MVP |  |  |  | 8 | 11 |  |  |  | 0
32 | LAUNCH | Develop MVP | Define Your Brand |  |  |  | 7 | 7 |  |  |  | 0
33 | LAUNCH | Develop MVP | Establish an Online Footprint |  |  |  | 9 | 9 |  |  |  | 0
34 | LAUNCH | Develop MVP | Create Design and Wireframes |  |  |  | 9 | 11 |  |  |  | 0
35 | LAUNCH | Develop MVP | Finish Logo and Creatives |  |  |  | 9 | 9 |  |  |  | 0
36 | LAUNCH | Raise (Pre-)Seed Capital | Consider Various Funding Options |  |  |  | 10 | 10 |  |  |  | 0
37 | LAUNCH | Raise (Pre-)Seed Capital | Calculate Required Funding Amount and Valuation |  |  |  | 10 | 10 |  |  |  | 0
38 | LAUNCH | Raise (Pre-)Seed Capital | Determine Non-Financial Investor Requirements |  |  |  | 10 | 10 |  |  |  | 0
39 | LAUNCH | Raise (Pre-)Seed Capital | Identify Relevant Investor Types |  |  |  | 10 | 11 |  |  |  | 0
40 | LAUNCH | Raise (Pre-)Seed Capital | Prepare and Pitch to Potential Investors |  |  |  | 10 | 13 |  |  |  | 0
41 | LAUNCH | Raise (Pre-)Seed Capital | Evaluate Potentially Interested Investors |  |  |  | 10 | 12 |  |  |  | 0
42 | LAUNCH | Raise (Pre-)Seed Capital | Secure (Pre-)Seed Investment |  |  |  | 11 | 16 |  |  |  | 0
43 | LAUNCH | Build Functions | Define Target Organization Chart |  |  |  | 11 | 11 |  |  |  | 0
44 | LAUNCH | Build Functions | Gather Requirements for Each Function |  |  |  | 11 | 12 |  |  |  | 0
45 | LAUNCH | Build Functions | Design Operating Model |  |  |  | 11 | 14 |  |  |  | 0
46 | LAUNCH | Build Functions | Incorporate Legal Entity |  |  |  | 11 | 11 |  |  |  | 0
47 | LAUNCH | Build Functions | Set Up Bank Account |  |  |  | 11 | 12 |  |  |  | 0
48 | LAUNCH | Build Functions | Set Up Accounting |  |  |  | 12 | 12 |  |  |  | 0
49 | LAUNCH | Build Functions | Define Central and Local Logistics Value Streams |  |  |  | 12 | 12 |  |  |  | 0
50 | LAUNCH | Build Functions | Select Payment Service Provider |  |  |  | 12 | 13 |  |  |  | 0
51 | LAUNCH | Build Functions | Register Trademark |  |  |  | 12 | 12 |  |  |  | 0
52 | LAUNCH | Build Functions | Perform Capacity Planning for Facility |  |  |  | 12 | 12 |  |  |  | 0
53 | LAUNCH | Build Functions | Set Up Content Production |  |  |  | 12 | 13 |  |  |  | 0
54 | LAUNCH | Build Functions | Build Supply Chain |  |  |  | 13 | 14 |  |  |  | 0
55 | LAUNCH | Build Functions | Organize Distribution |  |  |  | 13 | 14 |  |  |  | 0
56 | LAUNCH | Build Functions | Institute Sales Funnel |  |  |  | 13 | 14 |  |  |  | 0
57 | LAUNCH | Build Functions | Prepare Cross-Channel Marketing and Sales Strategy |  |  |  | 14 | 14 |  |  |  | 0
58 | LAUNCH | Build Functions | Ramp Up Facility |  |  |  | 14 | 14 |  |  |  | 0
59 | LAUNCH | Build Functions | Set Up Customer Care |  |  |  | 14 | 14 |  |  |  | 0
60 | LAUNCH | Build Functions | Prepare Tech Infrastructure and Security |  |  |  | 14 | 14 |  |  |  | 0
61 | LAUNCH | Set Up KPI Reports | Define Top 20 KPIs |  |  |  | 14 | 14 |  |  |  | 0
62 | LAUNCH | Set Up KPI Reports | Set Up Data Warehouse |  |  |  | 14 | 14 |  |  |  | 0
63 | LAUNCH | Set Up KPI Reports | Prepare Daily, Weekly, and Monthly Reports |  |  |  | 14 | 14 |  |  |  | 0
64 | LAUNCH | Set Up KPI Reports | Set Hiring Targets |  |  |  | 14 | 14 |  |  |  | 0
65 | LAUNCH | Go Live | Stress Test and Bug-Fix Across Functions |  |  |  | 14 | 14 |  |  |  | 0
66 | LAUNCH | Go Live | Prepare Press List |  |  |  | 14 | 14 |  |  |  | 0
67 | LAUNCH | Go Live | Start KPI Reporting |  |  |  | 14 | 15 |  |  |  | 0
68 | LAUNCH | Go Live | Conduct Launch PR Campaign and Paid Marketing |  |  |  | 14 | 15 |  |  |  | 0
69 | LAUNCH | Go Live | Continue Testing and Bug-Fixing |  |  |  | 14 | 15 |  |  |  | 0
70 | SCALE | Raise Growth Capital | Secure Growth Investment |  |  |  | 15 | 20 |  |  |  | 0
71 | SCALE | Raise Growth Capital | Set Up Employee Participation Program |  |  |  | 15 | 15 |  |  |  | 0
72 | SCALE | Build Culture | Design and Track Hiring Process |  |  |  | 15 | 15 |  |  |  | 0
73 | SCALE | Build Culture | Foster People Development |  |  |  | 15 | 20 |  |  |  | 0
74 | SCALE | Build Culture | Create and Maintain Company Culture |  |  |  | 15 | 20 |  |  |  | 0
75 | SCALE | Learn from Data | Navigate Using Daily, Weekly, and Monthly Reports |  |  |  | 15 | 15 |  |  |  | 0
76 | SCALE | Learn from Data | Dig Deeper Using Ad-hoc Reports for Each Function |  |  |  | 15 | 15 |  |  |  | 0
77 | SCALE | Learn from Data | Analyze Progress Toward Financial Targets |  |  |  | 15 | 15 |  |  |  | 0
78 | SCALE | Learn from Data | Focus on Cross-Channel Marketing Mix that Works |  |  |  | 15 | 16 |  |  |  | 0
79 | SCALE | Learn from Data | Analyze Customer Engagement with Product |  |  |  | 15 | 16 |  |  |  | 0
80 | SCALE | Learn from Data | Re-design Operating Model According to Data |  |  |  | 15 | 17 |  |  |  | 0
81 | SCALE | Learn from Data | Establish Proper Financial Reporting, Controlling, and Compliance |  |  |  | 15 | 18 |  |  |  | 0
82 | SCALE | Optimize Functions | Groom and Prioritize Product Roadmap |  |  |  | 16 | 16 |  |  |  | 0
83 | SCALE | Optimize Functions | Enhance UI/UX According to Usability Tests |  |  |  | 16 | 16 |  |  |  | 0
84 | SCALE | Optimize Functions | Boost Tech Stack’s Scalability, Availability, Speed, and Security |  |  |  | 16 | 16 |  |  |  | 0
85 | SCALE | Optimize Functions | Eliminate Operational Bottlenecks |  |  |  | 16 | 16 |  |  |  | 0
86 | SCALE | Optimize Functions | Re-assess Suppliers and Partners |  |  |  | 17 | 17 |  |  |  | 0
87 | SCALE | Optimize Functions | Optimize Payment Mix, Fees, Checkout Funnel and Fraud Prevention |  |  |  | 17 | 17 |  |  |  | 0
88 | SCALE | Optimize Functions | Improve Management of Sales Funnel |  |  |  | 17 | 17 |  |  |  | 0
89 | SCALE | Optimize Functions | Optimize CAC VS CLV |  |  |  | 17 | 18 |  |  |  | 0
90 | SCALE | Optimize Functions | Enhance CRM |  |  |  | 17 | 17 |  |  |  | 0
91 | SCALE | Optimize Functions | Build Brand and Execute PR Strategy |  |  |  | 18 | 18 |  |  |  | 0
92 | SCALE | Optimize Functions | Improve Customer Care Processes to Maximize NPS |  |  |  | 18 | 18 |  |  |  | 0
93 | SCALE | Optimize Functions | Automate Important Manual Processes |  |  |  | 18 | 18 |  |  |  | 0
94 | SCALE | Optimize Functions | Accelerate Workforce |  |  |  | 18 | 18 |  |  |  | 0
95 | SCALE | Best Practices | Phase in OKR System |  |  |  | 18 | 18 |  |  |  | 0
96 | SCALE | Best Practices | Define Best Practices for Each Function |  |  |  | 19 | 20 |  |  |  | 0
97 | SCALE | Independence | Implement Best Practices |  |  |  | 19 | 19 |  |  |  | 0
98 | SCALE | Independence | Implement Ongoing Knowledge Sharing |  |  |  | 19 | 20 |  |  |  | 0
99 | SCALE | Independence | Achieve Product-Market-Fit |  |  |  | 20 | 20 |  |  |  | 0
100 | SCALE | Independence | Constantly Evaluate Further Growth and Expansion Options |  |  |  | 20 | 20 |  |  |  | 0